## Slide 1: Group exercise 3: NHWA implementation roadmap
Health Workforce Department, WHO, Geneva

## Slide 2: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Governmental buy-in | Prepare report and make presentation to Policy Team of the MOH Prepare Cabinet Submission seeking endorsement for the multi-sectoral approach | Wednesday 24th July, 2019 August 1st, 2019 | Ministry of Health Ministry of Education Ministry of Finance (Statistics, Budget) Department of Public Administration Cabinet Secretary Cabinet Ministers

## Slide 3: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Governance | Develop TOR for and Appoint Multisectoral Group based on Cabinet approval Convene meeting of Multisectoral Group Develop Workplan/Action Plan of Multisectoral group | October 2019 November 2019 | Multisectoral Grouping – Government Ministries, Civil Society, Private Sector, Trade Unions

## Slide 4: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Scoping and Planning | Conduct assessment of HRHIS with the Ministry Gather information regarding data type held by other institutions/bodies Prepare report on findings and recommendations of HRHIS requirements Liaise with the Ministry of ICT to support system acquisition and implementation | September 2019 October 2019 | Ministry of Health, Depart. Of Public Administration, Ministry of Finance, Public Service Commission, Nurses & Midwives Council, Medical & Dental Council, Ministry of ICT, PAHO

## Slide 5: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Legal Framework | Based on Cabinet decision regarding the appointment of multisectoral group, seek advise from the Ministry of Legal Affairs to legal framework and obligations for information sharing Where possible amend respective legislation or develop MOUs to govern issue around information exchange/sharing Meet with members of the Multisectoral group to explain the legal obligations for information sharing | December 2019 January 2020 | Cabinet, Ministry of Legal Affairs; Ministry of Health

## Slide 6: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Data compilation and analysis | Develop and standardize data definitions Develop and formalize data flow based on the institutions responsible for data exchange Identify data entry group and Technical working group to validate data | December 2020 | Ministry of Health (Planning Unit, HR Unit) Statistics Division Ministry of ICT Dept of Public Administration

## Slide 7: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Validation | Compilation of data gathered for presentation to multisectoral group Presentation of data and analytical report to multisectoral group | March 2020 | Ministry of Health; Multisectoral Group
Dissemination |  |  | 
Process revision / sustainability |  |  |