## Slide 1: Group Exercise 3: NHWA Implementation Roadmap
Presented by : The Golden Sunshine Team /Jamaica
Gail Hudson
Howard Lynch
Karen Nelson
Health Workforce Department, WHO, Geneva
July 18,2019

## Slide 2: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Governmental buy-in | Prepare a briefing paper to support the need for the NHWA Do an inventory of all the relevant information systems to support NHWA Identify the stakeholder agencies and key stakeholders. | 10 working days 12 weeks 2 weeks | Focal Point /Snr Director of HRM&A Director Human Resource(HR) Department Director of HR

## Slide 3: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Governance | Conduct Stakeholder Mapping Request a nominee from each of the stakeholder agencies Set up a steering committee Set up a secretariat | 2 weeks 2 weeks 4 weeks 4 weeks | Focal Point /Snr Director of HRM&A Permanent Secretary Focal Point /Snr Director of HRM&A Focal Point /Snr Director of HRM&A

## Slide 4: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Scoping and planning | Technical working group conduct maturity assessment Prepare data analysis and dissemination plan Develop budget to support NHWA. Incorporate plan in the MOHW Operation Plan | 4 weeks 12 weeks 12 weeks 2 weeks | Technical working group Technical working group Technical working group Technical working group

## Slide 5: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Legal framework | Developing and negotiating a MOU with the data sources. Develop standard operating procedures to deal with data breach Develop standard operating procedures on how to share the results | 36 weeks 12 weeks 12 weeks | Director of the Legal Department Technical working group Technical working group

## Slide 6: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Data compilation and analysis | Conduct Quality assessment of all data sources Standards develop and adopted on data collection schedule and utilization. Identify potential new sources of data to answer evolving questions | 36 weeks 12 weeks 24 weeks | Technical working group Technical working group Technical working group

## Slide 7: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Validation | Plan and execute workshop Share the outcome of the validation exercise Prepare a user friendly report | 24 weeks 24 weeks 24 weeks | Steering Committee Steering Committee Steering Committee

## Slide 8: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Dissemination | Define the target audience Identify communication team to implement plan Develop a communication plan Monitoring effectiveness of HRH message | 4 weeks 8 weeks 6 weeks Ongoing | Technical working group Communication Team Communication Team Communication Team

## Slide 9: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Process revision / sustainability | Develop a monitoring and evaluation ( M&E)plan Conduct the evaluation Conduct a workshop for the dissemination of M&E findings | 8 weeks 12 weeks 6 weeks | Technical working group Technical working group Technical working group