## Slide 1: Group exercise 3: NHWA implementation roadmap
Saint Lucia
Health Workforce Department, WHO, Geneva
18 July, 2019

## Slide 2: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Governmental buy-in | Presentation to Policy Committee within the MOH to get buy-in for the highest level | Immediate | NHWA focal point Corporate Planning Unit (CPU) Statistics
Governance | - Meeting with the Multi-sectoral Committee | Medium term | Focal Point CPU
Scoping and planning |  | Medium term | Focal Point CPU Statistics
Legal framework | - Review the HRH Policy to incorporate NWHA | Medium term | Focal Point CPU Multi-sectoral Committee
Data compilation and analysis | Sensitize stakeholders of the NHWA Concept Inform them of their roles Train/introduce data entry people to use the platform | Medium to long term | Focal point Stakeholders (Min. of the Public Service (MoPS), Councils, Association, Statistics, etc) PAHO/WHO
Validation |  | Long term | - Focal Point
Dissemination |  | Long term | Focal Point Communications Unit
Process revision / sustainability |  | Long term | Focal Point CPU (M+E Team)