## Slide 1: Group exercise 3: NHWA implementation roadmap
Health Workforce Department, WHO, Geneva

## Slide 2: Group work 3
You are asked to do the following:
Work with colleagues from your own country (you can group together with another country with similar issues or work alone, if you are the only one from your country)
Using the template, prepare a roadmap with 3 to 5 key strategic actions towards NHWA implementation in your country
Identify timeline (immediate/ medium term/ long term) for the actions and key stakeholders to be involved
Send your slide to us by 9am tomorrow morning and prepare to present your roadmap (we will randomly select few)

## Slide 3: Roadmap with major steps to be developed
Steps | Actions | Timeline | Key actors in the country
Governmental buy-in | Prepare and present brief on NHWA to Minister and Cabinet colleagues | By August 31st 2019 | Chief Nursing Officer
Governance | Convene a meeting with key stakeholders Identify focal point, secretariat, devel- op, TWG, TOR, identify support staff, financing, policies and SOPs, communication team, legal advisor | By November 3o 2019 | Focal point as lead person, CNO, CMO, Rgistrar of nursing and medical councils, chief statistition, HID, MoL, ABNA, FBO
Scoping and planning | Map available data system and data systems, Determine gaps, develop plan to collect additional data, data dissemination plan | By March 2020 | TWG, focal point, CNO,
Legal framework | Develop MOUs between private and public sectors Specify data source, quality and completeness | By March 2020 | Focal point, CMO, CNO, Ministry of Legal Affairs
Data compilation and analysis | Establish NHWA. Identify data mining sources, Formalize mechanism for collecting data in the NHWA | By September 2020 | Focal point, TWG, CNO
Validation | Review data periodically Triangulate | By September 2020 | Focal point, TWG
Dissemination | Provide access to data by key stakeholders for policy formulation and decision making | By September 2020 | TWG, Focal Point
Process revision / sustainability | Review steps leading to developing and managing the NHWA Identify and fill gaps to improve efficiency and sustainability | Biennially | TWG, Focal Point